## Test Summary
Software version | 0.5.8 | Notes: Took binary file provided by bit on 4/13/2021. The version number was not changed, so the version of software may not be helpful in this case
UI Hardware Version
Main Control Hardware Version
Machine Serial Number (if applicable)
Test Summary
Subcategory | Number Of Tests | Tests Completed | Progress
Engineering Bench Tests
Technician Bench Tests
In Machine Testing
Total Completion

## Test Plan Revision History
Version | Notes
1.0.0 | Initial Test Plan
1.2.0 | Cleaned up the test plan (split out model B3 testing, and model B6 testing)

## Engineering Bench Tests
| Objective | Test Number | Proposal Test Method | Steps | Expected Result | Actual Result | Conclusion | Other Notes
1 | Determine method for getting current clock speed | 1 | Modify Clock Speed output. Read signal from oscilloscope | In file hpl_gclk_config.h, Set macro CONF_GCLK_GEN_0_OE to 1 |  |  | NA
|  |  |  | In file main.c Initialized PB14 as an output |  |  | NA
|  |  |  | In file main.c Set PB14 as clock output |  |  | NA
|  |  |  | Set a trap immediately following gpio initialization |  |  | NA
|  |  |  | Connected probe to PB14 | Clock output should be approximately 100 Mhz | Clock operating around 102 Mhz | Pass | See test 1 artifacts
2 | Verify watchdog operation (fault should trigger after 15 minutes) | 2 | Set trap in each thread and verify reset source | in main.c Add a breakpoint if reset controller detects watchdog fault |  |  | NA | if(hri_rstc_get_RCAUSE_WDT_bit(RSTC)) { asm("bkpt"); }
|  |  |  | In SystemManager.cpp Add trap in void SystemManager::systemManagementTask(void * parm) function | Controls reset after 15 minutes | Controls reset around 15s | INCONCLUSIVE
|  |  |  | In CapsenseController.cpp Add trap in void CapsenseController::touch_chip_task(void *p) | Controls reset after 15 minutes | Controls reset around 15s | INCONCLUSIVE
|  |  |  | In e54manageadc.c Add trap in void AdcConversionTask(void *p) | Controls reset after 15 minutes | Controls reset around 15s | INCONCLUSIVE
|  |  |  | In DispenseManager.cpp Add trap in void DispenseManager::coffeeDispenseTask(void * parm) | Controls reset after 15 minutes | Controls reset around 15s | INCONCLUSIVE
|  |  |  | In Warmer.cpp Add trap to void Warmer::warmingTask(void * parm) | Controls reset after 15 minutes | Controls reset around 15s | INCONCLUSIVE
|  |  |  | In TankManager.cpp Add trap to void TankManager::Manage_Fill_Task(void* parm_p) | Controls reset after 15 minutes | Controls reset around 15s | INCONCLUSIVE
|  |  |  | In TankManager.cpp Add trap to void TankManager::Manage_Temps_And_Heat_Task(void* parm_p) | Controls reset after 15 minutes | Controls reset around 15s | INCONCLUSIVE
|  |  |  | In ScreenManager.cpp Add trap to void ScreenManager::OS_Task(void * parm_p) | Controls reset after 15 minutes | Controls reset around 15s | INCONCLUSIVE

## Technician Bench Tests
| Objective | Test Number | Steps | Expected Result | Actual Result | Conclusion | Other Notes
1 | Verify thermistor curve data is correct | 1 | Connect resistor decade box to pins VCC and TMP on connector P6
Power up controls and go to view temperatures screen
|  |  | Set resistance to 5000 ohms | Should get an R value of 5000 +/- 5%
|  |  | Set resistance to 1000 ohms | Should get an R value of 1000 +/- 5%
|  |  | Set resistance to 500 ohms | Should get an R value of 500 +/- 5%
|  |  | Set resistance to 100 ohms | Should get an R value of 100 +/- 5%
Power cycle controls
|  |  | Set resistance to 5000 ohms | Should get an R value of 5000 +/- 5%
|  |  | Set resistance to 1000 ohms | Should get an R value of 1000 +/- 5%
|  |  | Set resistance to 500 ohms | Should get an R value of 500 +/- 5%
|  |  | Set resistance to 100 ohms | Should get an R value of 100 +/- 5%
2 | Verify water level data remains unchanged | 2 | Power up controls and go to view water levels screen
|  |  | Open circuit TGND and HI | "A" values between 2800 and 2900
|  |  | Open circuit TGND and LO | "A" values between 2800 and 2900
|  |  | Short circuit TGND and HI | "A" values between 0 - 100
|  |  | Short circuit TGND and LO | "A" values between 0 - 100
Power cycle controls
|  |  | Open circuit TGND and HI | "A" values between 2800 and 2900
|  |  | Open circuit TGND and LO | "A" values between 2800 and 2900
|  |  | Short circuit TGND and HI | "A" values between 0 - 100
|  |  | Short circuit TGND and LO | "A" values between 0 - 100
3 | Verify fill circuit timing | 3 | Power on controls
Wait until in normal state
Short circuit TGND and LO
Short cicuit TGND and Hi on connector P6
|  |  | Open circuit TGND and Hi on connector | Fill valve should open after 2s + 1s
Power cycle controls
Short circuit TGND and LO
Short cicuit TGND and Hi on connector P6
|  |  | Open circuit TGND and Hi on connector | Fill valve should open after 2s + 1s
4 | Verify recipe timing | 4
Set recipe to have 1 pulse with an on time of 120 seconds on B3 model
|  |  | Go into normal mode and start dispense | Dispense valve should be open for 120s +/- 1%
Set recipe to have 1 pulse with an on time of 120 seconds on left and right sides
|  |  | Go into normal mode and start dispense on left side | Dispense valve should be open for 120s +/- 1%
|  |  | Go into normal mode and start dispense on right side | Dispense valve should be open for 120s +/- 1%
|  |  | Perform dispense on both sides simultaneously | Both dispense valves should be open for 120s +/- 1%
Power cycle, repeat 2 more times
Set recipe to have 1 pulse with an on time of 120 seconds on B3 model
|  |  | Go into normal mode and start dispense | Dispense valve should be open for 120s +/- 1%
Set recipe to have 1 pulse with an on time of 120 seconds on left and right sides
|  |  | Go into normal mode and start dispense on left side | Dispense valve should be open for 120s +/- 1%
|  |  | Go into normal mode and start dispense on right side | Dispense valve should be open for 120s +/- 1%
|  |  | Perform dispense on both sides simultaneously | Both dispense valves should be open for 120s +/- 1%
Power cycle, repeat 2 more times

## In Machine Tests B3
These tests are to be performed on a B-Series B-3 |  | These tests are to be performed on a B-Series B-3
Model Number
Serial Number
| Objective | Test Number | Steps | Expected Result | Actual Result | Conclusion | Other Notes
| Verify touch operation | 1 | On B3 (record SN in "Other Notes" column)
Enter normal state
|  |  | Touch warmer 0 | Warmer should turn on
|  |  | Touch warmer 0 | Warmer should turn off
|  |  | Touch warmer 1 | Warmer should turn on
|  |  | Touch warmer 1 | Warmer should turn off
|  |  | Touch warmer 2 | Warmer should turn on
|  |  | Touch warmer 2 | Warmer should turn off
Enter normal state and allow machine to enter a ready state (filled, water temperature heated. etc)
On B3 (record SN in "Other Notes" column)
|  |  | Touch dispense button | Dispense cycle should start
|  |  | Touch dispense button | Dispense cycle should stop
|  |  | Press and hold "accept" key for 5 seconds | Should enter menus
|  |  | Press "next" key | Should go to next item in menu
|  |  | Press "previous" key | Should go to previous item in menu
|  |  | Press "cancel" key | Should return to normal state
Power cycle controls
Enter normal state
|  |  | Touch warmer 0 | Warmer should turn on
|  |  | Touch warmer 0 | Warmer should turn off
|  |  | Touch warmer 1 | Warmer should turn on
|  |  | Touch warmer 1 | Warmer should turn off
|  |  | Touch warmer 2 | Warmer should turn on
|  |  | Touch warmer 2 | Warmer should turn off
Enter normal state and allow machine to enter a ready state (filled, water temperature heated. etc)
On B3 (record SN in "Other Notes" column)
|  |  | Touch dispense button | Dispense cycle should start
|  |  | Touch dispense button | Dispense cycle should stop
Enter normal state and allow machine to enter a ready state (filled, water temperature heated. etc)
On B6 (record SN in "Other Notes" column)
|  |  | Touch left dispense button | Dispense cycle should start
|  |  | Touch left dispense button | Dispense cycle should stop
|  |  | Touch right dispense button | Dispense cycle should start
|  |  | Touch right dispense button | Dispense cycle should stop
|  |  | Press and hold "accept" key for 5 seconds | Should enter menus
|  |  | Press "next" key | Should go to next item in menu
|  |  | Press "previous" key | Should go to previous item in menu
|  |  | Press "cancel" key | Should return to normal state
Power cycle controls
| Verify saved settings | 2 | B3
Set up recipe pulses on to 30,31,32,33,34,35,36,37 for Pre infusion pulse to pulse 7 respectively Set up recipe pulse off to 10, 11, 12, 13, 14, 15, 16 for Pre infusion pulse to pulse 7 respectively
Power cycle machine
|  |  | Verify each pulse for recipe | Values for recipe remain set
Set tank temperature to random temperature (do not use the default value). Record in "Other Notes" column
Power cycle machine
|  |  | Verify set value from previous step | Value should remain set
Change time format to opposite format (ie if it is 12 hour format, change to 24 hour format). Note in the "Other Notes" column
Power cycle machine
|  |  | Verify set value from previous step | Value should remain set
Change Low temperature no brew to opposite format already set (ie if enabled, disable it)
Power cycle machine
|  |  | Verify set value from previous step | Value should remain set
Make changes to the energy savings format. Note changes to the "Other Notes" column
Power cycle machine
|  |  | Verify set value from previous step | Value should remain set
B3
Record current brew count in the menus
Complete a dispense cycle
Power cycle machine
|  |  | Verify brew count incremented | Value should increase per the amount of dispense cycles
B3
Set up recipe pulses on to 30,31,32,33,34,35,36,37 for Pre infusion pulse to pulse 7 respectively Set up recipe pulse off to 10, 11, 12, 13, 14, 15, 16 for Pre infusion pulse to pulse 7 respectively
Power cycle machine
|  |  | Verify each pulse for recipe | Values for recipe remain set
Set tank temperature to random temperature (do not use the default value). Record in "Other Notes" column
Power cycle machine
|  |  | Verify set value from previous step | Value should remain set
Change time format to opposite format (ie if it is 12 hour format, change to 24 hour format). Note in the "Other Notes" column
Power cycle machine
|  |  | Verify set value from previous step | Value should remain set
Change Low temperature no brew to opposite format already set (ie if enabled, disable it)
Power cycle machine
|  |  | Verify set value from previous step | Value should remain set
Make changes to the energy savings format. Note changes to the "Other Notes" column
Power cycle machine
|  |  | Verify set value from previous step | Value should remain set
B3
Record current brew count in the menus
Complete a dispense cycle
Power cycle machine
|  |  | Verify brew count incremented | Value should increase per the amount of dispense cycles
Post testing steps
Reteach each head
| LCD Driver verification | 3 | Verify message in normal state are displayed correctly for 3 seconds +/- .5s | Messages displayed for 3 seconds +/- .5 seconds
On B3
|  |  | Turn on each warmer | Warmer 0 On message displayed for 3 seconds +/- .5 seconds
Warmer 1 On message displayed for 3 seconds +/- .5 seconds
Warmer 2 On message displayed for 3 seconds +/- .5 seconds
|  | 4 | B3
|  |  | Verify warmer 0 timing | Warmer turns on for 7 mins, turns off for 3 minutes
|  |  | Verify warmer 1 timing | Warmer turns on for 7 mins, turns off for 3 minutes
|  |  | Verify warmer 2 timing | Warmer turns on for 7 mins, turns off for 3 minutes
B3
|  |  | Verify warmer 0 timing | Warmer turns on for 7 mins, turns off for 3 minutes
|  |  | Verify warmer 1 timing | Warmer turns on for 7 mins, turns off for 3 minutes
|  |  | Verify warmer 2 timing | Warmer turns on for 7 mins, turns off for 3 minutes
5 | Dispense Timing Verification | 5 | B3
Program recipe using teach mode
|  |  | Monitor dispense valve open time while while dispensing | Valve should be open per the recipe
B3
|  |  | Program recipe using teach mode | Valve should be open per the recipe
Monitor dispense valve open time while while dispensing
6 | Check for any general faults, or resets | 6 | B3
|  |  | Place machine in automatic mode at start of day | At end of day, no faults should be present on normal screen

## In Machine Tests B6
These tests are to be performed on a B-Series B-6
Model Number
Serial Number
| Objective | Test Number | Steps | Expected Result | Actual Result | Conclusion | Other Notes
|  | 1 | On B6 (record SN in "Other Notes" column
Enter normal state
|  |  | Touch warmer 0 | Warmer should turn on
|  |  | Touch warmer 0 | Warmer should turn off
|  |  | Touch warmer 1 | Warmer should turn on
|  |  | Touch warmer 1 | Warmer should turn off
|  |  | Touch warmer 2 | Warmer should turn on
|  |  | Touch warmer 2 | Warmer should turn off
|  |  | Touch warmer 3 | Warmer should turn on
|  |  | Touch warmer 3 | Warmer should turn off
|  |  | Touch warmer 4 | Warmer should turn on
|  |  | Touch warmer 4 | Warmer should turn off
|  |  | Touch warmer 5 | Warmer should turn on
|  |  | Touch warmer 5 | Warmer should turn off
Enter normal state and allow machine to enter a ready state (filled, water temperature heated. etc)
On B3 (record SN in "Other Notes" column)
|  |  | Touch dispense button | Dispense cycle should start
|  |  | Touch dispense button | Dispense cycle should stop
Enter normal state and allow machine to enter a ready state (filled, water temperature heated. etc)
On B6 (record SN in "Other Notes" column)
|  |  | Touch left dispense button | Dispense cycle should start
|  |  | Touch left dispense button | Dispense cycle should stop
|  |  | Touch right dispense button | Dispense cycle should start
|  |  | Touch right dispense button | Dispense cycle should stop
|  |  | Press and hold "accept" key for 5 seconds | Should enter menus
|  |  | Press "next" key | Should go to next item in menu
|  |  | Press "previous" key | Should go to previous item in menu
|  |  | Press "cancel" key | Should return to normal state
Power cycle controls
Enter normal state
|  |  | Touch warmer 0 | Warmer should turn on
|  |  | Touch warmer 0 | Warmer should turn off
|  |  | Touch warmer 1 | Warmer should turn on
|  |  | Touch warmer 1 | Warmer should turn off
|  |  | Touch warmer 2 | Warmer should turn on
|  |  | Touch warmer 2 | Warmer should turn off
On B6 (record SN in "Other Notes" column)
Enter normal state
|  |  | Touch warmer 0 | Warmer should turn on
|  |  | Touch warmer 0 | Warmer should turn off
|  |  | Touch warmer 1 | Warmer should turn on
|  |  | Touch warmer 1 | Warmer should turn off
|  |  | Touch warmer 2 | Warmer should turn on
|  |  | Touch warmer 2 | Warmer should turn off
|  |  | Touch warmer 3 | Warmer should turn on
|  |  | Touch warmer 3 | Warmer should turn off
|  |  | Touch warmer 4 | Warmer should turn on
|  |  | Touch warmer 4 | Warmer should turn off
|  |  | Touch warmer 5 | Warmer should turn on
|  |  | Touch warmer 5 | Warmer should turn off
Enter normal state and allow machine to enter a ready state (filled, water temperature heated. etc)
On B3 (record SN in "Other Notes" column)
|  |  | Touch dispense button | Dispense cycle should start
|  |  | Touch dispense button | Dispense cycle should stop
Enter normal state and allow machine to enter a ready state (filled, water temperature heated. etc)
On B6 (record SN in "Other Notes" column)
|  |  | Touch left dispense button | Dispense cycle should start
|  |  | Touch left dispense button | Dispense cycle should stop
|  |  | Touch right dispense button | Dispense cycle should start
|  |  | Touch right dispense button | Dispense cycle should stop
|  |  | Press and hold "accept" key for 5 seconds | Should enter menus
|  |  | Press "next" key | Should go to next item in menu
|  |  | Press "previous" key | Should go to previous item in menu
|  |  | Press "cancel" key | Should return to normal state
Power cycle controls
|  | 2 | B6
Left Side
Set up recipe pulses on to 30,31,32,33,34,35,36,37 for Pre infusion pulse to pulse 7 respectively Set up recipe pulse off to 10, 11, 12, 13, 14, 15, 16 for Pre infusion pulse to pulse 7 respectively
Power cycle machine
|  |  | Verify each pulse for recipe | Values for recipe remain set
Right Side
Set up recipe pulses on to 30,31,32,33,34,35,36,37 for Pre infusion pulse to pulse 7 respectively Set up recipe pulse off to 10, 11, 12, 13, 14, 15, 16 for Pre infusion pulse to pulse 7 respectively
Power cycle machine
|  |  | Verify each pulse for recipe | Values for recipe remain set
Set tank temperature to random temperature (do not use the default value). Record in "Other Notes" column
Power cycle machine
|  |  | Verify set value from previous step | Value should remain set
Change time format to opposite format (ie if it is 12 hour format, change to 24 hour format). Note in the "Other Notes" column
Power cycle machine
|  |  | Verify set value from previous step | Value should remain set
Change Low temperature no brew to opposite format already set (ie if enabled, disable it)
Power cycle machine
|  |  | Verify set value from previous step | Value should remain set
Make changes to the energy savings format. Note changes to the "Other Notes" column
Power cycle machine
|  |  | Verify set value from previous step | Value should remain set
B6
Complete a random number of dispense cycles on left side (use a count different from the other side). Note the count in the "Other Notes" column
Complete a dispense cycle on left side
Power cycle machine
|  |  | Verify brew count incremented | Value should increase per the amount of dispense cycles
Record current brew count in the menus
Complete a random number of dispense cycles on right side (use a count different from the other side). Note the count in the "Other Notes" column
Power cycle machine
|  |  | Verify brew count incremented | Value should increase per the amount of dispense cycles
Power cycle machine
B6
Left Side
Set up recipe pulses on to 30,31,32,33,34,35,36,37 for Pre infusion pulse to pulse 7 respectively Set up recipe pulse off to 10, 11, 12, 13, 14, 15, 16 for Pre infusion pulse to pulse 7 respectively
Power cycle machine
|  |  | Verify each pulse for recipe | Values for recipe remain set
Right Side
Set up recipe pulses on to 30,31,32,33,34,35,36,37 for Pre infusion pulse to pulse 7 respectively Set up recipe pulse off to 10, 11, 12, 13, 14, 15, 16 for Pre infusion pulse to pulse 7 respectively
Power cycle machine
|  |  | Verify each pulse for recipe | Values for recipe remain set
Set tank temperature to random temperature (do not use the default value). Record in "Other Notes" column
Power cycle machine
|  |  | Verify set value from previous step | Value should remain set
Change time format to opposite format (ie if it is 12 hour format, change to 24 hour format). Note in the "Other Notes" column
Power cycle machine
|  |  | Verify set value from previous step | Value should remain set
Change Low temperature no brew to opposite format already set (ie if enabled, disable it)
Power cycle machine
|  |  | Verify set value from previous step | Value should remain set
Make changes to the energy savings format. Note changes to the "Other Notes" column
Power cycle machine
|  |  | Verify set value from previous step | Value should remain set
B6
Complete a random number of dispense cycles on left side (use a count different from the other side). Note the count in the "Other Notes" column
Complete a dispense cycle on left side
Power cycle machine
|  |  | Verify brew count incremented | Value should increase per the amount of dispense cycles
Record current brew count in the menus
Complete a random number of dispense cycles on right side (use a count different from the other side). Note the count in the "Other Notes" column
Power cycle machine
|  |  | Verify brew count incremented | Value should increase per the amount of dispense cycles
Power cycle machine
Post testing steps
Reteach each head
3 | LCD Driver verification | 3 | Verify messages in normal state are displayed correctly for 3 seconds +/- .5s | Messages displayed for 3 seconds +/- .5 seconds
On B6
Warmer 0 On message displayed for 3 seconds +/- .5 seconds
Warmer 1 On message displayed for 3 seconds +/- .5 seconds
Warmer 2 On message displayed for 3 seconds +/- .5 seconds
Warmer 3 On message displayed for 3 seconds +/- .5 seconds
Warmer 4 On message displayed for 3 seconds +/- .5 seconds
Warmer 5 On message displayed for 3 seconds +/- .5 seconds
4 | Warmer Timing verification | 4
B6
|  |  | Verify warmer 0 timing | Warmer turns on for 7 mins, turns off for 3 minutes
|  |  | Verify warmer 1 timing | Warmer turns on for 7 mins, turns off for 3 minutes
|  |  | Verify warmer 2 timing | Warmer turns on for 7 mins, turns off for 3 minutes
|  |  | Verify warmer 3 timing | Warmer turns on for 7 mins, turns off for 3 minutes
|  |  | Verify warmer 4 timing | Warmer turns on for 7 mins, turns off for 3 minutes
|  |  | Verify warmer 5 timing | Warmer turns on for 7 mins, turns off for 3 minutes
B6
|  |  | Verify warmer 0 timing | Warmer turns on for 7 mins, turns off for 3 minutes
|  |  | Verify warmer 1 timing | Warmer turns on for 7 mins, turns off for 3 minutes
|  |  | Verify warmer 2 timing | Warmer turns on for 7 mins, turns off for 3 minutes
|  |  | Verify warmer 3 timing | Warmer turns on for 7 mins, turns off for 3 minutes
|  |  | Verify warmer 4 timing | Warmer turns on for 7 mins, turns off for 3 minutes
|  |  | Verify warmer 5 timing | Warmer turns on for 7 mins, turns off for 3 minutes
|  | 5 | B6 - Left
Program recipe using teach mode
|  |  | Monitor dispense valve open time while while dispensing | Valve should be open per the recipe
B6 - Right
Program recipe using teach mode
|  |  | Monitor dispense valve open time while while dispensing | Valve should be open per the recipe
B6 - Left
Program recipe using teach mode
|  |  | Monitor dispense valve open time while while dispensing | Valve should be open per the recipe
B6 - Right
Program recipe using teach mode
|  |  | Monitor dispense valve open time while while dispensing | Valve should be open per the recipe
6 | Check for any general faults, or resets | 6 | Place machine in automatic mode at start of day | At end of day, no faults should be present on normal screen

## Background
NA
PASS
FAILED
INCONCLUSIVE
List
NA